Enter a valid date
## LANDING PAGE
► OpenFRM

Version 2019.09.16

INTRO		The Open Financial Review Model (OpenFRM) is a tool to plan, coordinate and operate multi-apartment buildings. It is structured around five key financial aspects in such a development: Design, Build, Finance, Maintain & Operate. This gives (1) insight in the required initial investments, (2) the structure of financing for the investment, (3) the related cost structure over a period of 35 years, as well (4) a resulting Life Cycle Cost Analysis (LCCA) to assess the long-term viability of a project. / OpenFRM is primarily aimed at setting up of residential communities, especially housing / working co-operatives or co-housing projects, but can be adapted to other situations.

OpenFRM MODULES	BASE DATA	► INPUTS / OUTPUTS
		On the base of just a few input parameters, this module generates an initial overview of your project. As you add more detail in the respective segments of the spreadsheet, this will get reflected in the outputs.

	DBFMO	► DESIGN
		The design module lists an overview of the costs associated with the initial activities such as conceptualising a building and its community up to the final detailed technical 'blueprint' that will allow for the construction of an apartment building.

		► BUILD
		In the build module all the costs of physically realising your project are brought together. It gives also an insight in the different phases of the construction, allowing you to add detail as soon as the plans for the building get more concrete. Through this, you can make an initial estimate that can get more refined as you go.

		► FINANCE
		The finance sheet gives you an overview of the sources of capital required for the initial investment, as well as the costs associated with acquiring this capital. It features a loan calculator to review different credit scenarios.

		► MAINTAIN
		In this sheet, the costs of maintenance are listed. It provides an overview of the costs of upkeep and repair as a building goes through different life stages.

		► OPERATE
		This module shows the aspects of operating a building on a year-to-year basis. It lists the incoming payments from the users, as well as the costs of managing, administrating and running the building (utility costs, etc.).

	LCCA	► LIFE CYCLE COST ANALYSIS
		The LCCA module gives a 35-years overview of the economic aspects (investment, revenues, costs, etc) of a building. It allows for a detailed insight in the financial performance of the building, helping to make sure the viability of the investment for its community and it financiers.

INFO	HELP	You can find the OpenFRM manual here (will be added)

	CC-BY-SA 4.0	OpenFRM is open-source. You can freely use, modify and distribute it, as long as you release it under the same CC-BY-SA 4.0 conditions.

## INPUTS - OUTPUTS
H

► INPUTS / OUTPUTS module

INPUTS	BASE INFO REQUIRED	HOW MANY APARTMENTS?				0
		HOW MANY PEOPLE?				0
		m2 OF PRIVATE (APT.) SPACE PER PERSON?				0
		HOW MUCH OF TOTAL ADDITIONAL SHARED SPACE? (m2)				0
		HOW MUCH OF ADDITIONAL COMMERCIAL SPACE? (m2)				0
		ENTRY FEE (MEMBER DEPOSIT) PER APARTMENT?				0%
		ENERGY CLASS OF THE BUILDING				(OBLIGATORY ⊻ )
		ENERGY CLASS	total primary energy use [kWh/(m²a)]	space heating [kWh/(m²a)]	domestic electricity [kWh/(m²a)]	price of construction [gross, €/m²]	optional: non-electric source for heating [%]	select energy class – put “1” for selection
		Conventional building >	260	210	50	360	0%	0
		Energy Efficient >	120	70	50	415		0
		Passive House >	60	15	45	540		1
		Zero Energy >	15	0	15	630		0
		STARTING DATE OF YOUR PROJECT				2020-01-01
	OPTIONAL	DETAILED APARTMENT TYPOLOGY (“1” for YES, “0” for NO) ⊻ (unfold with '+' on left )				0
		apartment type		m2 / unit	occupants / unit	#
		TYPE 1		0	0	0
		TYPE 2		0	0	0
		TYPE 3		0	0	0
		TYPE 4		0	0	0
		TYPE 5		0	0	0
		TOTAL		0	0	0
		GROSS TO NET RATIO				0.0
		COMMUNICATION COEFFICIENT				0.0

OUTPUTS	BASIC OUTPUTS
	m2	TOTAL NET FLOOR AREA (m2)				0
		TOTAL GROSS FLOOR AREA (m2)				0
		TOTAL NET APT AREA (m2)				0
		TOTAL NET LETTABLE AREA (m2)				0
	EUR	TOTAL INVESTMENT (EUR)				0
		INVESTMENT /m2 NET (EUR)				0
		OWN CAPITAL				0
		LOAN REQUIRED				0
		TOTAL COST OF CAPITAL				0
		AVERAGE OPERATIONAL COSTS OF THE BUILDING (EUR per YEAR)				0
		AVERAGE RENT LEVEL (EUR per MONTH per m2, incl. operation)				0
	COSTS OVERVIEW ⊻ (unfold with '+' on left )

	INVESTMENT COSTS
	DESIGN	D 1 INITIATION			0	0
		D 2 COMMUNITY SETUP			0
		D 3 BUILDING DESIGN			0
	BUILD	B 1 SITE ACQUISITION			0	0
		B 2 SITE PREPARATION			0
		B 3 CONSTRUCTION IN PHASES			0
		B 4 BUILDING SUPERVISION			0
		B 5 PROOFING			0
		B 6 VAT			0
	TOTAL INVESTMENT COSTS					0

	OPERATING COSTS
	YEAR	O 1.1 FIXED SERVICE FEE	O 1.2 VARIABLE SERVICE FEE	O 1.3 CAPITAL FEE (EQUITY)			TOTAL EUR PER YEAR	EUR/m2/month with utilities	EUR/m2/month without utilities

	#			LOAN 1	LOAN 2	LOAN 3
	(development)	0	0	0	0	0	0	0	0
	1	0	0	0	0	0	0	0	0
	2	0	0	0	0	0	0	0	0
	3	0	0	0	0	0	0	0	0
	4	0	0	0	0	0	0	0	0
	5	0	0	0	0	0	0	0	0
	6	0	0	0	0	0	0	0	0
	7	0	0	0	0	0	0	0	0
	8	0	0	0	0	0	0	0	0
	9	0	0	0	0	0	0	0	0
	10	0	0	0	0	0	0	0	0
	11	0	0	0	0	0	0	0	0
	12	0	0	0	0	0	0	0	0
	13	0	0	0	0	0	0	0	0
	14	0	0	0	0	0	0	0	0
	15	0	0	0	0	0	0	0	0
	16	0	0	0	0	0	0	0	0
	17	0	0	0	0	0	0	0	0
	18	0	0	0	0	0	0	0	0
	19	0	0	0	0	0	0	0	0
	20	0	0	0	0	0	0	0	0
	21	0	0	0	0	0	0	0	0
	22	0	0	0	0	0	0	0	0
	23	0	0	0	0	0	0	0	0
	24	0	0	0	0	0	0	0	0
	25	0	0	0	0	0	0	0	0
	26	0	0	0	0	0	0	0	0
	27	0	0	0	0	0	0	0	0
	28	0	0	0	0	0	0	0	0
	29	0	0	0	0	0	0	0	0
	30	0	0	0	0	0	0	0	0
	31	0	0	0	0	0	0	0	0
	32	0	0	0	0	0	0	0	0
	33	0	0	0	0	0	0	0	0
	34	0	0	0	0	0	0	0	0
	35	0	0	0	0	0	0	0	0
	AVERAGE OPERATING COSTS (YEAR / M2 WARM / M2 COLD )					0	0.00	0.00

OPTIONAL OUTPUTS	AVERAGE MONTHLY PAYMENT PER APARTMENT TYPE DURING LIFE TIME OF THE BUILDING, IF DETAILED APARTMENT TYPOLOGY IS USED (⊻)
	apartment type			m2 / unit	# of units	TOTAL monthly pay per unit	BASIC RENT	SERVICES and UTILITIES	DEPOSIT
	TYPE 1			-	-	0	0	0	0
	TYPE 2			-	-	0	-	0	0
	TYPE 3			-	-	0	-	0	0
	TYPE 4			-	-	0	-	0	0
	TYPE 5			-	-	0	-	0	0
	TOTAL / AVERAGE			-	-	0	0	0	0

NUMBERS TO COMPARE WITH THE MARKET PRICE LEVELS >					rent including utilities per m2	basic rent per m2	services and utilities per m2
					0	0	0

## DESIGN
► DESIGN module					UNIT	AMOUNT	PRICE / UNIT	TOTAL COST

D 1 INITIATION (⊻)					0
D 1.1 KICK-START TEAM FEES					fee	0	0	0
D 1.2 OUTREACH (PR / MARKETING)					campaign	0	0	0
D 2 COMMUNITY SETUP (⊻)					0
D 2.1 ORGANISATIONAL SETUP					0
D 2.1.1 REGISTERING THE COOP					tax	1	0	0
D 2.1.2 RUNNING DURING 24 MONTHS					monthly costs	24	0	0
D 2.2 COMMUNITY FORMATION TRAJECTORY					meeting	0	0	0
D 3 BUILDING DESIGN (⊻)					0
D 3.1 PROGRAMMATIC DESIGN					workshops	0	0	0
D.3.2 FEASIBILITY STUDY					0
D 3.2.1 LOCATION PLANNING CONDITIONS					fee	0	0	0
D 3.2.2 TECHNICAL ASSESSMENTS					study	0%	0	0
D 3.2.3 PRELIMINARY DESIGN					project	0%	0	0
D 3.3 PROJECT DOCUMENTATION FOR BUILDING PERMIT					project	0%	0	0
D 3.4 TECHNICAL DESIGN					0
D 3.4.1 DETAILED PLANNING					fee/m2	0	0	0
D 3.4.2 LICENSING					fee	0	0	0
D 3.4.3 PLANNING SUPERVISION					fee	0%	0	0

				DESIGN SUM			0

## BUILD
► BUILD module					UNIT	AMOUNT	PRICE	TOTAL COST

B 1 SITE ACQUISITION (⊻)					0
B 1.1 LAND ACQUISITION					m2	0	0	0
B 1.2 PROPERTY REGISTRATION FEE					fee	1	0	0
B 1.3 TAXES CADASTER					fee	1	0	0
B 1.4 TAXES ON LAND ACQUISITION					fee	0.00%	0	0
B 2 SITE PREPARATION (⊻)					0
B 2.1 CONSTRUCTION LAND FEE					m2	0	0	0
B 2.2 INFRASTRUCTURE PREPARATIONS					0
B 2.2.1 WATER					fee	1	0	0
B 2.2.2 SEWAGE					fee	1	0	0
B 2.2.3 ELECTRICITY					fee	1	0	0
B 2.3 SITE SET UP
B 3 CONSTRUCTION IN PHASES					m2	0	540	0
optional > CALCULATE BASED ON DETAILED BREAKDOWN instead of m2 average (⊻)					0
B 3.1 FOUNDATION					0	0
B 3.2 FLOOR STRUCTURE					0	0
B 3.3 WALL STRUCTURE					0	0
B 3.4 EXTERIOR FINISHING					0	0
B 3.5 ROOF AND COVER					0	0
B 3.6 INSTALLATIONS					0	0
B 3.6.1 PLUMBING					0	0
B 3.6.2 SEWAGE					0	0
B 3.6.3 HEATING					0	0
B 3.6.4 VENTILATION					0	0
B 3.6.5 PV					0	0
B 3.6.6 HIGH VOLTAGE INSTALLATIONS - ELECTRICITY					0	0
B 3.6.7 LOW VOLTAGE INSTALLATIONS - PHONE, INTERNET, TV, ...					0	0
B 3.7 INTERIOR FINISHING					0	0
B 3.7.1 WALLS					0	0
B 3.7.2 FLOORS					0	0
B 3.7.3 CEILINGS					0	0
B 3.8 FURNISHING					0	0
B 3.8.1 WINDOWS					0	0
B 3.8.2 DOORS					0	0
B 3.8.3 KITCHEN EQUIPMENT					0	0
B 3.8.4 TOILET/BATHROOM EQUIPMENT					0	0
B 3.8.5 POWER OUTLETS					0	0
B 3.8.6 SWITCHES AND LIGHTS					0	0
B 3.9 OUTDOOR ARRANGEMENT					0	0
B 3.9.1 CAR ACCESS AND PARKING					0	0
B 3.9.2 WALKING PATHS					0	0
B 3.9.3 GREENERY					0	0
B 3.10 DELIVERY OF BUILDING					0	0
B 3.10.1 SITE CLEAN UP					0	0
B 4 BUILDING SUPERVISION					fee	0%	0	0
B 5 PROOFING (⊻)					0
B 4.1 ENERGY CERTIFICATE					elaborat	0	0	0
B 4.2 TAXES AND USE PERMIT					0
B 4.2.1 ADMINISTRATIVE TAX FOR USE PERMIT					fee	0	0	0
B 4.2.2 CADASTER REGISTRATION FEE					fee	0	0	0
B 4.2.3 TECHNICAL PROOFING OF THE BUILDING					fee	0.00%	0	0
B 6 VAT (add if required)

				BUILD SUM			0

## FINANCE
► FINANCE module					UNIT	AMOUNT	PRICE	TOTAL

F 1 REQUIRED CAPITAL (⊻)					0
F 1.1 GRANTS					1	0	0
F 1.2 DONATIONS					0	0%	0
F 1.3 MEMBERSHIP					non-refundable fee	0	0	0
F 1.4 MEMBER DEPOSIT					refundable fee	0	0%	0
F 1.5 LOANS (⊻)					0
DETAILED FINANCIAL INPUT
INPUTS >	F 1.5.1 LOAN 1 ("TISE")					F 1.5.2 LOAN 2 ("COMMERCIAL BANK LOAN")					F 1.5.3 LOAN 3 ("FRIENDLY LOAN")
	LOAN SIZE					0	LOAN SIZE					0	LOAN SIZE					0
	LOAN TERM IN YEARS					0	LOAN TERM IN YEARS					0	LOAN TERM IN YEARS					0
	FINANCIAL PHASES IN YEARS	- - -	- - -	- - -	- - -	- - -	- - -	FINANCIAL PHASES IN YEARS	1 - 5	6 - 10	11 - 15	16 - 20	21 - 25	26 - 30	FINANCIAL PHASES IN YEARS	1 - 5	6 - 10	11 - 15	16 - 20	21 - 25	26 - 30

	ANNUAL INTEREST RATE	- %	- %	- %	- %	- %	- %	ANNUAL INTEREST RATE	0.00%	0.00%	0.00%	0.00%	0.00%	0.00%	ANNUAL INTEREST RATE	0%	0%	0%	0%	0%	0%
	TAKEN IN MONTH - 'start after' (max 12)					0	TAKEN IN MONTH - 'start after' (max 12)					0	TAKEN IN MONTH - 'start after' (max 12)					0
	In case of GRACE PERIOD type 1, otherwise leave 0					0	In case of GRACE PERIOD type 1, otherwise leave 0					0	In case of GRACE PERIOD type 1, otherwise leave 0					0
	GRACE PERIOD - in months					0	GRACE PERIOD - in months					0	GRACE PERIOD - in months					0
	ADDITIONAL FINANCIAL BUFFER (borrowed)					0	ADDITIONAL FINANCIAL BUFFER (borrowed)					0	ADDITIONAL FINANCIAL BUFFER (borrowed)					0
DETAILED FINANCIAL OUTPUT
	F 1.5.1 LOAN 1 ("TISE")					F 1.5.2 LOAN 2 ("COMMERCIAL BANK LOAN")					F 1.5.3 LOAN 3 ("FRIENDLY LOAN")
month	installment	interest	principal	remaining princ.	interest rate	yearly sum		installment	interest	principal	remaining princ.	interest rate	yearly sum		installment	interest	principal	remaining princ.	interest rate	yearly sum
0	(€)	(€)	(€)	0.00€	%	(€)		(€)	(€)	(€)	0.00€	%	(€)		(€)	(€)	(€)	0.00€	%	(€)
1	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
2	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
3	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
4	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
5	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
6	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
7	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
8	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
9	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
10	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
11	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
12	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
13	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
14	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
15	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
16	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
17	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
18	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
19	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
20	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
21	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
22	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
23	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
24	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
25	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
26	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
27	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
28	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
29	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
30	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
31	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
32	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
33	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
34	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
35	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
36	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
37	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
38	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
39	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
40	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
41	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
42	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
43	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
44	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
45	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
46	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
47	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
48	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
49	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
50	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
51	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
52	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
53	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
54	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
55	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
56	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
57	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
58	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
59	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
60	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
61	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
62	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
63	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
64	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
65	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
66	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
67	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
68	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
69	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
70	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
71	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
72	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
73	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
74	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
75	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
76	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
77	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
78	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
79	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
80	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
81	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
82	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
83	0	0	0	0	0.0%	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
84	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
85	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
86	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
87	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
88	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
89	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
90	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
91	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
92	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
93	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
94	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
95	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
96	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
97	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
98	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
99	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
100	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
101	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
102	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
103	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
104	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
105	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
106	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
107	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
108	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
109	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
110	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
111	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
112	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
113	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
114	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
115	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
116	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
117	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
118	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
119	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
120	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
121	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
122	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
123	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
124	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
125	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
126	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
127	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
128	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
129	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
130	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
131	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
132	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
133	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
134	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
135	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
136	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
137	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
138	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
139	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
140	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
141	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
142	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
143	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
144	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
145	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
146	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
147	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
148	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
149	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
150	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
151	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
152	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
153	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
154	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
155	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
156	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
157	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
158	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
159	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
160	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
161	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
162	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
163	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
164	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
165	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
166	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
167	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
168	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
169	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
170	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
171	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
172	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
173	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
174	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
175	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
176	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
177	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
178	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
179	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
180	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
181	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
182	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
183	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
184	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
185	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
186	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
187	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
188	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
189	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
190	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
191	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
192	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
193	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
194	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
195	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
196	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
197	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
198	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
199	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
200	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
201	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
202	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
203	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
204	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
205	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
206	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
207	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
208	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
209	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
210	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
211	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
212	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
213	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
214	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
215	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
216	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
217	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
218	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
219	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
220	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
221	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
222	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
223	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
224	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
225	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
226	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
227	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
228	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
229	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
230	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
231	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
232	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
233	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
234	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
235	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
236	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
237	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
238	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
239	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
240	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
241	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
242	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
243	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
244	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
245	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
246	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
247	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
248	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
249	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
250	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
251	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
252	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
253	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
254	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
255	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
256	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
257	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
258	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
259	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
260	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
261	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
262	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
263	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
264	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
265	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
266	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
267	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
268	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
269	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
270	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
271	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
272	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
273	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
274	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
275	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
276	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
277	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
278	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
279	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
280	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
281	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
282	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
283	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
284	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
285	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
286	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
287	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
288	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
289	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
290	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
291	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
292	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
293	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
294	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
295	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
296	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
297	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
298	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
299	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
300	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
301	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
302	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
303	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
304	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
305	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
306	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
307	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
308	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
309	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
310	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
311	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
312	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
313	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
314	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
315	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
316	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
317	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
318	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
319	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
320	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
321	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
322	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
323	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
324	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
325	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
326	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
327	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
328	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
329	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
330	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
331	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
332	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
333	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
334	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
335	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
336	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
337	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
338	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
339	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
340	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
341	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
342	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
343	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
344	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
345	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
346	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
347	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
348	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
349	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
350	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
351	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
352	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
353	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
354	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
355	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
356	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
357	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
358	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
359	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
360	0	0	0	0	0	0		0	0	0	0	0.00%	0		0	0	0	0	0%	0
361	0	0	0	0	0	0		0	0	0	0	0	0		0	0	0	0	0	0
362	0	0	0	0	0	0		0	0	0	0	0	0		0	0	0	0	0	0
363	0	0	0	0	0	0		0	0	0	0	0	0		0	0	0	0	0	0
364	0	0	0	0	0	0		0	0	0	0	0	0		0	0	0	0	0	0
365	0	0	0	0	0	0		0	0	0	0	0	0		0	0	0	0	0	0
366	0	0	0	0	0	0		0	0	0	0	0	0		0	0	0	0	0	0
367	0	0	0	0	0	0		0	0	0	0	0	0		0	0	0	0	0	0
368	0	0	0	0	0	0		0	0	0	0	0	0		0	0	0	0	0	0
369	0	0	0	0	0	0		0	0	0	0	0	0		0	0	0	0	0	0
370	0	0	0	0	0	0		0	0	0	0	0	0		0	0	0	0	0	0
371	0	0	0	0	0	0		0	0	0	0	0	0		0	0	0	0	0	0
372	0	0	0	0	0	0		0	0	0	0	0	0		0	0	0	0	0	0
373	0	0	0	0	0	0		0	0	0	0	0	0		0	0	0	0	0	0
374	0	0	0	0	0	0		0	0	0	0	0	0		0	0	0	0	0	0
375	0	0	0	0	0	0		0	0	0	0	0	0		0	0	0	0	0	0
376	0	0	0	0	0	0		0	0	0	0	0	0		0	0	0	0	0	0
377	0	0	0	0	0	0		0	0	0	0	0	0		0	0	0	0	0	0
378	0	0	0	0	0	0		0	0	0	0	0	0		0	0	0	0	0	0
379	0	0	0	0	0	0		0	0	0	0	0	0		0	0	0	0	0	0
380	0	0	0	0	0	0		0	0	0	0	0	0		0	0	0	0	0	0
381	0	0	0	0	0	0		0	0	0	0	0	0		0	0	0	0	0	0
382	0	0	0	0	0	0		0	0	0	0	0	0		0	0	0	0	0	0
383	0	0	0	0	0	0		0	0	0	0	0	0		0	0	0	0	0	0
384	0	0	0	0	0	0		0	0	0	0	0	0		0	0	0	0	0	0
385	0	0	0	0	0	0		0	0	0	0	0	0		0	0	0	0	0	0
386	0	0	0	0	0	0		0	0	0	0	0	0		0	0	0	0	0	0
387	0	0	0	0	0	0		0	0	0	0	0	0		0	0	0	0	0	0
388	0	0	0	0	0	0		0	0	0	0	0	0		0	0	0	0	0	0
389	0	0	0	0	0	0		0	0	0	0	0	0		0	0	0	0	0	0
390	0	0	0	0	0	0		0	0	0	0	0	0		0	0	0	0	0	0
391	0	0	0	0	0	0		0	0	0	0	0	0		0	0	0	0	0	0
392	0	0	0	0	0	0		0	0	0	0	0	0		0	0	0	0	0	0
393	0	0	0	0	0	0		0	0	0	0	0	0		0	0	0	0	0	0
394	0	0	0	0	0	0		0	0	0	0	0	0		0	0	0	0	0	0
395	0	0	0	0	0	0		0	0	0	0	0	0		0	0	0	0	0	0
396	0	0	0	0	0	0		0	0	0	0	0	0		0	0	0	0	0	0
397	0	0	0	0	0	0		0	0	0	0	0	0		0	0	0	0	0	0
398	0	0	0	0	0	0		0	0	0	0	0	0		0	0	0	0	0	0
399	0	0	0	0	0	0		0	0	0	0	0	0		0	0	0	0	0	0
400	0	0	0	0	0	0		0	0	0	0	0	0		0	0	0	0	0	0

F 1.5.3 CROWD COMMUNITY					1	0	0
F 1.5.4 OTHER					1	0	0
F 2 OVERVIEW COSTS OF CAPITAL (⊻)					0
F 2.1 BANK PROCESSING					0
F 2.1.1 BANK PROCESSING COSTS					fee	1	0	0
F 2.1.2 INTEREST LOAN 1					monthly	0	0	0
F 2.1.3 INTEREST LOAN 2					monthly	0	0	0
F 2.1.3 INTEREST LOAN 3					monthly	0	0	0
F 2.2 PAYMENT PROTECTION INSURANCE					0

				TOTAL CAPITAL REQUIRED			0

				TOTAL COSTS OF CAPITAL			0

## MAINTAIN & OPERATE
► MAINTAIN & OPERATE module					UNIT	AMOUNT	PRICE	TOTAL COST / Y

O 1 CASH IN (⊻)					0
O 1.1 FIXED SERVICE FEE					yearly fee	1	0	0
O 1.2 VARIABLE SERVICE FEE					yearly fee	1	0	0
O 1.3.CAPITAL FEE (EQUITY)					yearly fee	1	0	0
O 1.4 OTHER REVENUES					0
O 1.4.1 EXTERNAL OR COMMERCIAL RENT					monthly rent	12	0	0
INPUTS >	SIZE of RENTABLE SPACE (m2)			RENT PRICE (EUR/M2/MONTH)
	0			0
O 1.4.2 CONSULTANCY					service fee	1	0	0
O 1.4.3 BAR, etc.					monthly earn	1	0	0
O 1.4.4 TEMPORARY OPERATIONAL BUFFER					yearly fee	1	0	0
O 1.4.5 ENERGY PRODUCTION					monthly production	12	0	0
O 1.5 INVESTMENT FUND					yearly fee	1	0	0
O 2 CASH OUT (⊻)					0
[FIXED COSTS:]					0
O 2.1 ADMINISTRATION					0
O 2.1.1 MANAGEMENT COSTS					monthly fee	12	0	0
O 2.1.2 OFFICE COSTS					monthly costs	12	0	0
O 2.1.3 MARKETING / PUBLIC RELATIONS					monthly fee	12	0	0
O 2.1.4 ACCOUNTING					yearly fee	1	0	0
O 2.2 COMMUNITY					monthly costs	12	0	0
O 2.3 LAND LEASE					monthly costs	12
O 2.4 OWNERSHIP TAX					yearly tax	1	0	0
O 2.5 BANK SERVICE CHARGES					monthly fee	12	0	0
O 2.6 INSURANCE					yearly policy	1	0	0
[VARIABLE COSTS:]					0
O 2.7 CLEANING (⊻)					service charges			0
O 2.7.1 INTERIOR					monthly service charges / apt	0	0	0
O 2.7.2 EXTERIOR					yearly charges / m2 apt	0	1	0
O 2.8 DIRECT MAINTENANCE AND REPAIRS					incidental cost	0	0	0
O 2.9 LONG TERM MAINTENANCE FUND					yearly charges	0%	0	0
O 2.10 UTILITIES					0
O 2.10.1 ENERGY					yearly costs	1	0	0
INPUTS >	Primary energy demand [kWh/(m²a)]		non-electric source for heating [%]		PRICE (EUR/kWh)
				ELECTRICITY	OTHER (e.g. GAS)
	60		0%		0.00	0.00
O 2.10.2 WATER					monthly costs	12	0	0
INPUTS >	Water usage (m3/person/month)			PRICE OF WATER (EUR/m3)
	4			0
O 2.10.3 SEWAGE					monthly costs	12	0	0
INPUTS >	Total water usage (m3/month)			PRICE (EUR/m3 of used water)
	0			0
O 2.10.4 GARBAGE COLLECTION					monthly costs	12	0	0
INPUTS >	Total size of the building (m2)			PRICE (EUR/NETm2)
	0			0
O 2.11 REHOUSING COSTS					monthly contribution	12	0	0
O 2.12 HOUSING VOID COVER					monthly contribution	12	0	0
[CAPITAL COSTS:]					0
O.2.13 BANK FEES AND TAXES DURING CREDIT					monthly fee	12	0	0
O 2.14 INTEREST - LOAN 1					monthly sum	12	0	0
O 2.15 INTEREST - LOAN 2					monthly sum	12	0	0
O 2.16 INTEREST - LOAN 3					monthly sum	12	0	0
O 2.17 PRINCIPAL REPAYMENT - LOAN 1					monthly sum	12	0	0
O 2.18 PRINCIPAL REPAYMENT - LOAN 2					monthly sum	12	0	0
O 2.19 PRINCIPAL REPAYMENT - LOAN 3					monthly sum	12	0	0

				AVERAGE CASH IN			0
				AVERAGE CASH OUT			0

				OPERATIONAL PROFIT / Y			0
				PROFIT TAX / Y		15%	0

## LCCA
CREDIT PERIOD OF			0	YEARS	DEVELOPMENT PHASE (< >)					EXPLOITATION PHASE
►LIFE CICLE COST ANALYSIS - LCCA (35 YEARS)
				01/01/2019	01/04/2019	01/07/2019	01/10/2019	01/01/2020	01/04/2020	01/07/2020	01/10/2020	01/01/2021	01/01/2021	01/01/2022	01/01/2023	01/01/2024	01/01/2025	01/01/2026	01/01/2027	01/01/2028	01/01/2029	01/01/2030	01/01/2031	01/01/2032	01/01/2033	01/01/2034	01/01/2035	01/01/2036	01/01/2037	01/01/2038	01/01/2039	01/01/2040	01/01/2041	01/01/2042	01/01/2043	01/01/2044	01/01/2045	01/01/2046	01/01/2047	01/01/2048	01/01/2049	01/01/2050	01/01/2051	01/01/2052	01/01/2053	01/01/2054	01/01/2055
				1.QUARTER	2.QUARTER	3.QUARTER	4.QUARTER	0	1.QUARTER	2.QUARTER	3.QUARTER	4.QUARTER	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	32	33	34	35
				(TOTAL)					(TOTAL)
CASH BALANCE - BEGINNING (=)					0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0

CASH IN (⊻)
INVESTMENT (ONE-TIME)					0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
F 1.1 GRANTS					0				0					0
F 1.2 DONATIONS					0				0					0
F 1.3 MEMBERSHIP					0				0					0
F 1.4 MEMBER DEPOSIT					0	0				0
F 1.5 LOAN 1 (to be placed accordingly to the dynamic dev. plan)					0	0				0
F 1.5 LOAN 2 (to be placed accordingly to the dynamic dev. plan)					0	0				0
F 1.5 LOAN 3 (to be placed accordingly to the dynamic dev. plan)					0	0				0
OPERATION (RECURRING)					0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
O 1.1 FIXED SERVICE FEE					0					0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
O 1.2 VARIABLE SERVICE FEE					0					0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
O 1.3 CAPITAL FEE (EQUITY)					0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
O 1.4 OTHER REVENUES					0					0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
O 1.5 INVESTMENT FUND					0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
TOTAL CASH IN (+)					0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0

CASH OUT (⊻)
INVESTMENT (ONE-TIME)					0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
D 1 INITIATION					0				0					0
D 2 COMMUNITY SETUP					0	0	0	0	0	0	0	0	0	0
D 3 BUILDING DESIGN					0		0					0
B 1 SITE ACQUISITION					0	0				0
B 2 SITE PREPARATION					0	0				0
B 3 CONSTRUCTION IN PHASES (to be placed accordingly to the dynamic dev. plan)					0	0	0	0	0	0
B 4 BUILDING SUPERVISION					0	0	0	0
B 5 PROOFING					0				0	0
B 6 VAT (add if required)					0				0	0
OPERATION (RECURRING)					0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
[FIXED COSTS]
O 2.1 ADMINISTRATION					0					0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
O 2.2 COMMUNITY					0					0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
O 2.3 LAND LEASE					0					0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
O 2.4 OWNERSHIP TAX					0					0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
O 2.5 BANK CHARGES					0					0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
O 2.6 INSURANCE					0					0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
[VARIABLE COSTS]
O 2.7 CLEANING					0					0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
O 2.8 DIRECT MAINTENANCE AND REPAIRS					0					0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
O 2.9 LONG TERM MAINTENANCE FUND					0					0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
O 2.10 UTILITIES					0					0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
O 2.11 REHOUSING COSTS					0					0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
O 2.12 HOUSING VOID COVER					0					0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
[CAPITAL COSTS]
O 2.13 BANK FEES AND TAXES DURING CREDIT					0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
O 2.14 INTEREST - LOAN 1					0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
O 2.15 INTEREST - LOAN 2					0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
O 2.16 INTEREST - LOAN 3					0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
INCOME TAX				15%					0					0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
TOTAL CASH OUT (-)					0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
O 2.17 PRINCIPAL REPAYMENT - LOAN 1					0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
O 2.18 PRINCIPAL REPAYMENT - LOAN 2					0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
O 2.19 PRINCIPAL REPAYMENT - LOAN 3					0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0

CASH FLOW (CASH IN - CASH OUT) (=)					0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0

CASH BALANCE - END (=)					0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0

INCOME STATEMENT (⊻):
Revenues					0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
Costs					0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
EBITDA					0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
Depreciation					0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
Interest					0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
Profit / Loss					0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
Income Tax					0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
Net Profit					0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0

MAINTAINANCE AND REPAIR FUND
DIRECT MAINTENANCE AND REPAIRS					0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
ACCUMULATED RESOURCES OVER TIME					0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0